## Slide 1
REFERENCE IMPLEMENTATION / DELIVERY PLAN
TaskFlow
A task management platform for a marketing agency
PREPARED FOR COMPANY 31 / MANUEL / MAY 2026

## Slide 2
What we'll cover
01
Solution architecture
Production diagram, technology choices, NFRs, and the assumptions behind them.
02
Delivery plan
Phased roadmap, team shape, top risks, and how we'd surface trouble early.
03
Technical leadership
Ways of working, handling a pushy PO, and what I'd ask on day one.
The companion repo is the reference implementation. This deck explains the choices behind it.
TASKFLOW / COMPANY 31 / MAY 2026
02 / 19

## Slide 3
Assumptions I'm working from
SCALE
Around 50 to 200 users initially, for one agency. Steady-state, not spiky.
TENANCY
Single tenant on day one. The design admits multi tenant later.
REGION
UK and EU data residency presumed. Marketing data is personal data.
LATENCY
Sub 300ms p95 for screen loads is plenty. This is not a trading app.
REALTIME
Not a launch requirement. We model commands and events so it bolts on cleanly.
HOSTING
Azure preferred (matches the .NET stack). Agnostic where it costs us little.
These are inputs, not conclusions. Each becomes a day one question (see slide 16).
TASKFLOW / COMPANY 31 / MAY 2026
03 / 19

## Slide 4
SECTION 01
Solution architecture
Production architecture, technology choices, and the trade-offs behind each.

## Slide 5
Production architecture, top down
USERS
Azure Front Door / Cloudflare / WAF, TLS termination, DDoS protection
Static SPA
Angular bundle on Blob Storage + CDN
.NET 8 API
Containerised / Azure Container Apps / 2 to 10 replicas
Identity provider. Entra ID or Auth0, OIDC into JWT bearer.
PostgreSQL
Azure DB / daily PITR / read replica
Redis
Sessions, rate limit, cache
Blob storage
Attachments, audit exports
OpenTelemetry into Application Insights or Honeycomb
Key Vault / managed identities
TASKFLOW / COMPANY 31 / MAY 2026
05 / 19

## Slide 6
Technology choices and trade-offs
LAYER | CHOICE | WHY AND TRADE-OFF
Frontend | Angular 18 (standalone, signals) | Batteries included, strict TS by default. Heavier bundle than React, fine at this scale.
Backend | .NET 8 minimal APIs | LTS until Nov 2026, fast, mature ecosystem. Swap to Controllers if the team prefers.
Database | PostgreSQL | Open, mature, JSONB if we need flexibility. SQL Server would work; Postgres is cheaper and more portable.
Auth | OIDC + JWT bearer | Works with whatever IdP the agency has. We're not in the auth business.
Runtime | Azure Container Apps | Managed scale to zero, no Kubernetes ops overhead. Vendor coupling abstracted behind IaC.
Observability | OpenTelemetry | Standardised, swappable backend (App Insights, Honeycomb, Grafana Cloud).
CI/CD | GitHub Actions + Bicep | Same repo, same review surface. Bicep over Terraform when Azure only.
TASKFLOW / COMPANY 31 / MAY 2026
06 / 19

## Slide 7
How the architecture addresses non functionals
Security
OIDC into JWT bearer, short lived tokens, refresh on the gateway.
Secrets in Key Vault via managed identity. None in env files.
WAF in front, dependabot and Snyk on PRs.
Tenant scoping enforced at the repository layer.
Scalability
Stateless API, horizontal scale on CPU and RPS metrics.
Database read replica for reporting workloads.
Redis for hot reads (board view, user lookups).
Cursor pagination on list endpoints from day one.
Reliability
Health probes (liveness vs readiness).
Blue and green deploys with automated rollback on SLO burn.
Database PITR plus nightly logical backups off region.
Retries with jitter. Circuit breaker on third parties.
Observability
Structured logs (Serilog) with traceId per request.
OpenTelemetry traces: browser into API into database.
RED metrics plus SLOs per endpoint.
Alert on burn rate, not on threshold spikes.
TASKFLOW / COMPANY 31 / MAY 2026
07 / 19

## Slide 8
SECTION 02
Delivery plan
Roadmap, team shape, the risks we'll watch, and how we'll know early.

## Slide 9
Phased roadmap, prototype to launch
NOW
Phase 0 / Foundation
Reference repo, ADRs, environments wired
Discovery workshops (users, integrations)
Auth provider and hosting confirmed
WK 1 to 3
Phase 1 / MVP
Auth, multi user, tasks, assignment, due dates
CI/CD, staging, structured logs, traces
Manual UAT with three client users
WK 4 to 6
Phase 2 / Beta
Comments, notifications, attachments
Real time updates (SignalR)
Performance and accessibility audit
WK 7 to 9
Phase 3 / Launch
Security review, pen test remediation
SLOs and alerting, runbooks written
Phased rollout (10%, 50%, 100%)
WK 10+
Phase 4 / Iterate
Feedback driven backlog
Tech debt budget (10 to 15% per sprint)
Quarterly architecture review
TASKFLOW / COMPANY 31 / MAY 2026
09 / 19

## Slide 10
Team composition
Core, full time
Tech lead (me). Code, architecture, stakeholders.
2 full stack engineers (mid or senior). Vertical slice delivery.
Senior frontend with UX leaning. Pattern library, accessibility, performance.
Shared, part time
DevOps and platform (~50%). IaC, pipelines, on call.
Designer (~25%). Flows, tokens, accessibility.
QA (~50% from Phase 2). Exploratory and automation.
Client side
Product owner with real authority over scope.
Two to three pilot users for weekly demos and UAT.
Why this shape
Small enough for one stand-up. Big enough for sustained pace.
Seniority spread enables mentorship without bottlenecks.
Specialists arrive when their work is the bottleneck, not before.
TASKFLOW / COMPANY 31 / MAY 2026
10 / 19

## Slide 11
Top risks and how we'll mitigate them
RISK | LIKELIHOOD / IMPACT | MITIGATION
Scope creep, the "just one more" | High / Med | Strict MVP definition, change control via PO, weekly demos surface trade-offs early.
Auth provider undecided by client | Med / High | OIDC abstraction lets us swap; day one question. Default to Entra ID if undecided.
Data migration from current workflows | Med / High | Discovery in week one; if non trivial, build an importer in Phase 2, not as a launch blocker.
Hidden compliance requirement (GDPR/ICO) | Low / High | Privacy review with legal in week one; data model with PII flags plus export/delete from day one.
Realtime becomes a launch must have | Med / Med | API built around commands and queries; SignalR layers on without changing the data model.
Key person dependency | Med / High | Pair programming, rotating reviewers, ADRs and runbooks in repo.
TASKFLOW / COMPANY 31 / MAY 2026
11 / 19

## Slide 12
How I'll surface delivery issues early
Cadence
Two week sprints; Friday demos to PO and pilot users.
Daily 15 minute stand-up. Risks and blockers first, status second.
Weekly written status: RAG, top three risks, asks.
Engineering metrics
DORA: lead time, deploy frequency, MTTR, change failure rate.
PR cycle time and review latency on the dashboard.
Flaky test budget enforced. No green on retry merges.
Product signals
Burn up of MVP scope vs target launch.
Weekly tag up with pilot users for qualitative feedback.
Post deploy error rate and latency dashboards on Monday.
Surfacing problems
RAG status is honest, not optimistic. Amber early beats red late.
If a sprint slips, the deliverable changes, not the date.
Blameless post mortems for incidents over 30 minutes.
TASKFLOW / COMPANY 31 / MAY 2026
12 / 19

## Slide 13
SECTION 03
Technical leadership
Standards, contentious conversations, and what I'd ask on day one.

## Slide 14
Setting the team up for success
Ways of working
Trunk based dev, short lived branches, daily merges.
Pair on risky/new work; mob occasionally for shared learning.
Tech debt time blocked weekly. Not optional.
Decisions recorded as ADRs in repo, not in chat.
Technical standards
Strict TypeScript, nullable refs, warnings as errors.
OpenAPI is the API contract. Client types generated.
Every new endpoint ships with an integration test.
Logs are structured. No Console.WriteLine.
Code review
1 approver for low risk; 2 for prod paths, schema, or auth.
PR description first. Reviewer reads it before the diff.
Reviews timely (4 hour target). Slow review kills flow.
Comments split into blocking / nit / question.
Definition of Done
Tests written and passing locally and in CI.
Deployed to staging. Observable in logs and traces.
Accessibility spot check (WCAG 2.1 AA). User docs updated.
Feature flag in place if rollback is not trivial.
TASKFLOW / COMPANY 31 / MAY 2026
14 / 19

## Slide 15
"The PO wants this feature now, but it's risky"
01
Acknowledge the goal.
The feature exists because of a real outcome the PO needs. Start there, not at "no".
02
Make the risk concrete.
What breaks? Who's affected? What's the blast radius? Numbers, not adjectives.
03
Offer options, not roadblocks.
A smaller scope. A time boxed spike. A flag protected rollout. Always two paths.
04
Quantify "fast" vs "safe".
Days, not feelings. The PO can choose with eyes open.
05
If they still push.
Write the decision and risks as an ADR; explicit sign-off; ship behind a kill-switch with heightened monitoring.
06
Never.
Say "no" as the engineer alone, or "yes" without the trade-off visible to whoever owns the budget.
TASKFLOW / COMPANY 31 / MAY 2026
15 / 19

## Slide 16
What I'd ask on day one
About the users
Who actually uses this? Roles, team sizes, technical comfort?
What does a busy day look like today?
Which of email/calls/meetings do they want to replace vs supplement?
About the data
Where does work live today? Spreadsheets, inboxes, tools?
Anything to import on day one, or do we start fresh?
Are the agency's clients ever exposed to this app?
About hosting and identity
Existing cloud provider and identity (Entra, Google, Okta)?
UK/EU data residency required? PII categories present?
Existing security/platform standards to inherit?
About launch and success
What does v1 success look like? Measurable?
Who decides scope when pressure to add more arrives?
What's the budget for ongoing operation post launch?
TASKFLOW / COMPANY 31 / MAY 2026
16 / 19

## Slide 17
How I'd answer them in the first two weeks
WEEK 1
Workshops.
90 minute sessions per user role; observe a typical day on site or shadow remote calls.
WEEK 1
Written discovery.
Existing docs, policies, integration touch points; security/IT alignment.
WEEK 2
Wireframes.
Low fi mockups validated with pilot users before any code beyond the prototype.
WEEK 2
ADRs published.
Auth provider, hosting region, data model approach. Written down and signed off.
ONGOING
Assumption log.
Anything we couldn't answer is logged with a target date for resolution.
TASKFLOW / COMPANY 31 / MAY 2026
17 / 19

## Slide 18
Concerns I would raise about the brief and prototype
!
"Production ready" is undefined.
We need explicit acceptance criteria: uptime, security, accessibility, observability targets.
!
No identity model in the prototype.
Real auth plus tenant scoping reshape every endpoint. Front-load this; it is not bolt-on.
!
No hosting or compliance constraint.
Marketing data is personal data. GDPR is in scope by default. Pin this down day one.
!
"Coordinate" is broader than tasks.
Email, calls, meetings imply notifications, mentions, summaries. Clarify what's v1 vs Phase 2.
!
Likely a multi app workflow.
Slack or Teams integration may be unavoidable. Confirm in week one before architectural choices bake in.
TASKFLOW / COMPANY 31 / MAY 2026
18 / 19

## Slide 19
IN SUMMARY
"Production ready" isn't a checkbox.
It's a small team shipping every week, behind feature flags, with the trade-offs written down where everyone can see them.
COMPANION REPO / GITHUB.COM/C31LABS/GLOBAL360ASSIGNEMENT